## 10-Sprint Plan
Phase | Deliverables/Outcome | Outcome | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12
Phase 1 – FE Automation (POC) | BDD-based FE (mobile native) automation framework; CI/CD integration. Tools: Detox, Appium, Maestro | FE automation framework delivered and integrated into CI/CD for pilot product. | POC + Framework Setup | CI/CD Integration Pilot Rollout (1 Product)
Phase 2 – Accessibility Testing (POC) | BDD-based accessibility automation framework CI/CD integration Tools: axe-core, Lighthouse. Accessibility automation integrated into CI/CD. | Accessibility automation integrated into CI/CD. |  | POC + Framework Setup | CI/CD Integration Pilot Rollout (1 Product)
Phase 3 – BE Automation (POC) | BDD-based BE (API) automation framework CI/CD integration Tools: REST Assured, Postman; evaluate JS/TS tools (Playwright API, PactumJS, SuperTest). | BE automation framework delivered and integrated into CI/CD for pilot product. |  |  | POC + Framework Setup | CI/CD Integration Pilot Rollout (1 Product)
Phase 4 – Product-Level E2E | BDD-based product-level E2E automation in shell app Tools: Detox + API automation (REST Assured / JS-TS tool). | Product-level E2E coverage integrated into CI/CD. |  |  | Framework Setup | CI/CD Integration Pilot Rollout (1 Product)
Phase 5 – Test Data Management | Test data management solution | Reusable, consistent test data sets available for test automation.
Phase 6 – System-Level E2E | BDD-based multi-product flow automation. Tools: Detox + API automation (REST Assured / JS-TS tool). | System-level E2E coverage integrated into CI/CD. |  |  |  |  | Framework Setup | CI/CD Integration Pilot Rollout (Multiple Products)
Phase 7 – FMEA | Risk-based testing practice Prioritised failure modes simulation playbook. | FMEA process defined and piloted. |  |  |  |  | Define | Pilot
Phase 7 – OAT | Operational readiness tests (failover, recovery, scaling) Runbook. | OAT checks automated in pipelines. | [5 empty] | Define | Pilot
Cross-cutting - Test Strategy | QE test strategy (living document), Test Practices QE Review gates. | Strategy applied across all phases; refined each sprint. | Strategy (Parallel) | Strategy (Parallel) | Strategy (Parallel) | Strategy (Parallel) | Strategy (Parallel) | Strategy (Parallel) | Strategy (Parallel) | Strategy (Parallel) | Strategy (Parallel) | Strategy (Parallel)
Cross-cutting - Unified Framework | Cross-platform unified automation framework (FE, BE, a11y, performance) and shared libraries. | Unified framework in place across platforms; reused by squads. | Unified (Parallel) | Unified (Parallel) | Unified (Parallel) | Unified (Parallel) | Unified (Parallel) | Unified (Parallel) | Unified (Parallel) | Unified (Parallel) | Unified (Parallel) | Unified (Parallel)
Future Phase - Web Desktop UI Automation | Web desktop UI automation framework. Tools: Playwright / Selenium. | Not in Scope for Current Sprints.
Future Phase - Mobile Web UI Automation | Mobile web UI automation framework Tools: Playwright / Appium hybrid. | Not in Scope for Current Sprints.